## Sheet1
| Requirement | Subtasks | Story Point Estimation | Dependency | Internal Comments | Q to Client
1 | Create the Employment Opportunity with the appropriate models, fields, and questionnaire. | Plug in the models, fields, and questionnaire into the current solution | 2
…
2+
2 | Allow open enrollment (unlike MTSI, which is invite-only). Students and organisations should be able to join after onboarding. Students will be restricted based on the URL of their email and whether their university is a UniConnected partner. | Onboarding process definition | 1 | 3 |  | 1. What is open enrollment process? How is it different from the current enrollment process? 2. What is the current onboarding process? Is it for uni only?
|  | Validation logic | 3
…
4+
3 | Introduce a University model so that only students with UniMelb email domains can initially join. | Introduce a University model so that only students with UniMelb email domains can initially join. | 1
…
1
4 | Generalise the Discover page into a reusable component, with a navigation dropdown for multiple opportunities. | Refactoring of the current code based for the reusable components | 3
|  | Create the navigation dropdown | 2
…
5
5 | Build the Discover Employment page with filters and search for both students and organisations. | Build the Discover Employment page | 4
|  | Implement filters | 2
|  | Implement search | 2
…
8
6 | Implement a paywall system for organisations, limiting filters/results based on subscription level. | Dashboard to look into the revenue and current subscription | 8 |  | 1. Not preferred, requirements not clear 2. Might be good for cross-team collaboration | 1. UI needed for the dashboard 2. Subscription model unclear
|  | Filtering/Restriction of certain UI elements | 6 |  |  | 1. Need to consider user interaction of each individual components 2. Subscription model unclear
…
14
7 | Provide APIs, models, and Swagger documentation, along with unit tests to ensure reliability. |  |  |  |  | 1. Perform in regular interval during the sprint across teams